## Slide 1: EDU-VET
E-Learning, Digitisation and Units for Learning at VET schools – Creating online Learning Environments in Technical Education for European metal industry
EDU-VET Curriculum and Online Course Meeting 16th- 18th of March 2021
Project Number: 2019-1-DE02-KA202-006068
Welcome and current status of EDU-VET
The European Commission support for the production of this publication does not constitute an endorsement of the contents which reflects the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein.

## Slide 2
EDU-VET Welcome and current status of EDU-VET
EDU-VET – Curriculum and Online Course Meeting Online Project Meeting 16th to 18th of March 2021
Project Number: 2019-1-DE02-KA202-006068
The European Commission support for the production of this publication does not constitute an endorsement of the contents which reflects the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein.

## Slide 3: Agenda of EDU-VET Meeting
1) Welcome and Current Status of EDU-VET in general
2) Current Status of EDU-VET in the countries
3) IO2: Curriculum and EDU-VET Moodle platform
4) IO3: Development of Tasks for EDU-VET courses
5) IO4: First Insights into EDU-VET Handbook
6) IO5: Online Observatory
7) IO6: First Insights into Policy Paper
8) What´s laying ahead of us?
9) Dissemination and exploitation
10) Meeting Evaluation

## Slide 4: Current status of EDU-VET in general
Current status of IOs
Project timeline – IOs
Project timeline – Project Meetings

## Slide 5: Current status of IOs
IO1: Summary Research Report
  Leading Organisation: UPB
  Duration: 01/09/2019 to 01/09/2020
IO2: Technical Education Curriculum for metal industry
  Leading Organisation: Berufskolleg Bocholt-West
  Duration: 01/10/2019 to 01/12/2020
IO3: Online Courses for Technical education in metal industry
  Leading Organisation: Ingenious Knowledge GmbH
  Duration: 01/02/2020 to 30/09/2021
IO4: Handbook and Guidelines for teachers
  Leading Organisation: Stichting BVE Oost-Gelderland
  Duration: 01/12/2020 to 31/10/2021
IO5: Showcases of best practice in eLearning at VET Schools
  Leading Organisation: Centro Integrado de Formación Profesional Someso
  Duration: 01/01/2020 to 30/09/2021
IO6: EDU-VET - Policy Paper with recommendations to policy makers
  Leading Organisation: Lancaster and Morecambe College
  Duration: 01/01/2021 to 31/10/2021

## Slide 6: Current status of IO1
IO1: Summary Research Report
Part 1: Desktop Research: Done ✓
  Research Report (per partner) ✓
Part 2: Field-based Research: Done ✓
  Interviews (4 partners)
  Questionnaire (100 participants per partner; Online Survey)
Writing Summary Pedagogic Research Report: Done ✓
Translations of Research Report into national languages: In progress
Creation of flipbook (IK): In progress

## Slide 7: Current status of IO2
IO2: Technical Education Curriculum for metal industry
Developing Curricular Framework: Done ✓
  1) Learning Outcome Matrix ✓
  2) Modules for the VET training measures ✓
  3) Overview of the tasks (H5P) ✓
Matching Learning Outcome Matrices: Done ✓
Matching Curriculum with existing sullabi in partner countries: Done ✓
  Writing a report on this (max. 5 pages; orientation on Curricular Framework and completed LOMs)
Development of Curriculum: In progress
  UPB and BKBW will write a report on the curriculum and create a paper brochure

## Slide 8: Current status of IO2
Development of Curriculum – Module structure
Entry Drilling UK
Entry Turning ES
Entry Milling NL
Advanced Drilling / Turning
Advanced Drilling / Milling
Advanced Turning / Milling
Experiences Drilling / Turning / Milling 1
Experiences Drilling / Turning / Milling 2
Experiences Drilling / Turning / Milling 3
Andree will cooperate with each partner

## Slide 9: Current status of IO2
Structure and contents of Curriculum:
Curriculum Report as basis for the EDU-VET Curriculum
In summary, the curriculum will be structured with three fundamental pillars:
  Pillar 1) EDU-VET Process model
  Pillar 2) EDU-VET Curriculum skill level model
  Pillar 3) EDU-VET Curriculum learning unit model

## Slide 10: Current status of IO3
IO3: Online Courses for technical education in metal industry
Creation of learning units (for online and classroom scenarios): In progress
  Development of content design
  Development of task design
  Development of interactive tasks
  Development of quizzes, questionnaires
  Development of video and audio design etc.
Creation of H5P and Moodle tasks: In progress
  Creation of online tasks via H5P (testing phase; creation of the prototypes on H5P)
  Creation of real tasks at Moodle (There will be an additional online meeting)
Content design of tasks (IK): In progress
Providing partner and introduction videos (all schools): In progress

## Slide 11: Current status of IO4
IO4: Handbook and Guidelines for teachers
Distribution of the book structure and distribution of the chapters to the partners: Done ✓
Writing of book chapters: In progress
Developing a framework regarding the guideline concept for teachers: In progress
Writing of guideline concept for teachers: In progress
Correction and Translation of handbook and guidelines: Starts soon

## Slide 12: Current status of IO5
IO5: Showcases of best practice in eLearning at VET Schools
Creation of criteria setting for Online Observatory: Done ✓
Provide guidelines to partner: Done ✓
Translation of Business Profile in own language: Done ✓
Technical implementation and development of technical infrastructure of Online Observatory: In progress
Searching for best-practices (metal companies) which can be presented on Online Observatory: In progress
  Each partner should acquire about 5 to 6 companies
  Companies should fill in the guideline and answer the questions
  The completed profiles of companies should be sent back UPB
  Translation of company profiles in English

## Slide 13: Current status of IO6
IO6: EDU-VET - Policy Paper with recommendations to policy makers
  Start: 01/01/2021
  First discussions about content and structure will be planned during the online meeting
  The Project Work Plan provides more details concerning next steps and activities for IO6

## Slide 14: Project timeline – IOs

Start 01/09/2019
Intellectual Output 3:
Feb 20 – Oct 21
Intellectual Output 2:
Oct 19- Dec 20
Intellectual Output 1:
Sep 19 – Sep 20
Project Management Sep 2020 – March 2022
1st Quarter
2nd Quarter
3rd Quarter
4th Quarter
2019
2020
2021
Dec
2019
March
2022
Intellectual Output 4:
Dec 20 – Oct 21
Intellectual Output 5:
Jan 20 – Sep 21
Dec
2021
2022
Sep
2019
Intellectual Output 6:
Jan 21 – Oct 21
Dec
2020
End 31/03/2022

## Slide 15: Project timeline – Project Meetings

Start 01/09/2019
M2 – 2nd Project Meeting in UK (LMC)
April 2020 (postponed)
M1 – Kick-Off Conference in GER (UPB) Nov 2019
1st Quarter
2nd Quarter
3rd Quarter
4th Quarter
2019
2020
2021
Dec
2019
March
2022
M3 – 3nd Project Meeting in Spain (CIFP
Sep 2020
M4 – 4th Project Meeting in NL (SBEOG)
May 21
Dec
2021
2022
Sep
2019
Multiplier Event
April 21 – Sep 21
Dec
2020
End 31/03/2022
M5 – 5th Project Meeting in GER (BKBW)
Oct 21

## Slide 16: Project timeline – Multiplier Events
E1
UPB, Germany
In total 4 Multiplier Events
Between August 2021 to December 2021
25 participants per country
1 day workshop
E2
SBEOG, Netherlands
E3
CIFP, Spain
E4
LMC, United Kingdom

## Slide 17: Project timeline – Multiplier Events
Online Multiplier Events are possible (depending on the current situation)
Creation of Multiplier Event Report
  1 page (short summary of what was discussed and the results of the multiplier event )
  Pictures or screenshots
  PPT Slides / PPT presentation
  Participation list
Content:
  Part A: Insight into the current situation of eLearning and digitalisation
  Part B: Insights into authentic approaches in VET using the EDU-VET online-showroom
  Part C: Chances and challenges for VET with regard to the EDU-VET curriculum and the EDU-VET modules and courses
  Part D: Results of the EDU-VET research
  Part E: Didactical and pedagogical hints and insights into EDU-VET Book
  Part F: Future perspectives and policy recommendations

## Slide 18
Contact
Marc Beutner University Paderborn, Warburger Str. 100 33098 Paderborn, Germany Marc.Beutner@uni-paderborn.de
http://wiwi.uni-paderborn.de/department5/ wirtschaftspaedagogik-prof-beutner/
The European Commission support for the production of this publication does not constitute an endorsement of the contents which reflects the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein.
  Do you have any questions?