## Slide 1: EDU-VET
E-Learning, Digitisation and Units for Learning at VET schools – Creating online Learning Environments in Technical Education for European metal industry
EDU-VET – Steering Committee Meeting
16th of March 2021, 3p.m to 5p.m. CET
Project Number: 2019-1-DE02-KA202-006068
3rd Steering Committee - Meeting
The European Commission support for the production of this publication does not constitute an endorsement of the contents which reflects the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein.

## Slide 2
EDU-VET 3rd Steering Committee - Meeting
EDU-VET – Steering Committee Meeting
16th of March 2021, 3p.m to 5p.m. CET
Project Number: 2019-1-DE02-KA202-006068
The European Commission support for the production of this publication does not constitute an endorsement of the contents which reflects the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein.

## Slide 3: Agenda
Extension of project duration
  Addendum for Grant Agreement
  Further project work under corona conditions
Project Timeline
  Current status of IOs
  Transnational meetings
  Multiplier Events

## Slide 4: Extension of project duration
Extension of project duration:
Due to the current Corona situation the EDU-VET project will be extended.
The duration of the project will run until 31/03/2022.
Addendum for Grant Agreement: Confirmed by NA on 10th of August 2020
Project duration: 01/09/2019 to 31/03/2022 (31 months)

## Slide 5: Extension of project duration
Further project work under Corona conditions:
Meetings can be held online:
  Local Working Group Meetings
  Transnational Meetings
  Multiplier Events
  Interviews with best-practices concerning IO5
Confirmation by NA on 08th of July 2020

## Slide 6: Current status of IOs
IO1: Summary Research Report
  Leading Organisation: UPB
  Duration: 01/09/2019 to 01/09/2020
IO2: Technical Education Curriculum for metal industry
  Leading Organisation: Berufskolleg Bocholt-West
  Duration: 01/10/2019 to 01/12/2020
IO3: Online Courses for Technical education in metal industry
  Leading Organisation: Ingenious Knowledge GmbH
  Duration: 01/02/2020 to 30/09/2021
IO4: Handbook and Guidelines for teachers
  Leading Organisation: Stichting BVE Oost-Gelderland
  Duration: 01/12/2020 to 31/10/2021
IO5: Showcases of best practice in eLearning at VET Schools
  Leading Organisation: Centro Integrado de Formación Profesional Someso
  Duration: 01/01/2020 to 30/09/2021
IO6: EDU-VET - Policy Paper with recommendations to policy makers
  Leading Organisation: Lancaster and Morecambe College
  Duration: 01/01/2021 to 31/10/2021
Ongoing
Ongoing
Ongoing
Ongoing
Starts soon
Ongoing

## Slide 7: Project timeline – IOs

Start 01/09/2019
Intellectual Output 3:
Feb 20 – Oct 21
Intellectual Output 2:
Oct 19- Dec 20
Intellectual Output 1:
Sep 19 – Sep 20
Project Management Sep 2020 – March 2022
1st Quarter
2nd Quarter
3rd Quarter
4th Quarter
2019
2020
2021
Dec
2019
March
2022
Intellectual Output 4:
Dec 20 – Oct 21
Intellectual Output 5:
Jan 20 – Sep 21
Dec
2021
2022
Sep
2019
Intellectual Output 6:
Jan 21 – Oct 21
Dec
2020
End 31/03/2022
Due to the project extension, the project timeline still needs to be adjusted!

## Slide 8: Project timeline – Project Meetings

Start 01/09/2019
M2 – 2nd Project Meeting in UK (LMC)
April 2020 (postponed)
M1 – Kick-Off Conference in GER (UPB) Nov 2019
1st Quarter
2nd Quarter
3rd Quarter
4th Quarter
2019
2020
2021
Dec
2019
March
2022
M3 – 3nd Project Meeting in Spain (CIFP
Sep 2020
M4 – 4th Project Meeting in NL (SBEOG)
May 21
Dec
2021
2022
Sep
2019
Multiplier Event
April 21 – Sep 21
Dec
2020
End 31/03/2022
M5 – 5th Project Meeting in GER (BKBW)
Oct 21
Due to the project extension, the project timeline still needs to be adjusted!
Due to the Corona situation, all meetings have to be conducted online!

## Slide 9: Project timeline – Multiplier Events
Due to the Corona situation, Multiplier Events have to be conducted online!
E1
UPB, Germany
E2
SBEOG, Netherlands
E3
CIFP, Spain
E4
LMC, United Kingdom
Online Multiplier Events are possible (depending on the current situation)
Creation of Multiplier Event Report
  1 page (short summary of what was discussed and the results of the multiplier event )
  Pictures or screenshots
  PPT Slides / PPT presentation
  Participation list

## Slide 10
Contact
Marc Beutner University Paderborn, Warburger Str. 100 33098 Paderborn, Germany Marc.Beutner@uni-paderborn.de
http://wiwi.uni-paderborn.de/department5/ wirtschaftspaedagogik-prof-beutner/
The European Commission support for the production of this publication does not constitute an endorsement of the contents which reflects the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein.
  Do you have any questions?